## Sheet1
Student Name |  | Benjamin Schubert
Student ID |  | a1627462
Principal Supervisor |  | Will Robertson
Proposed Thesis Title |  | Application of repulsive magnetism in designing optimised energy harvesting devices
|  |  | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
# | Component |  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
1 | Milestones
Annual Review | bar: 2017 O; 2018 O; 2019 O
Submission | bar: 2020 M
2 | Literature review | bar: 2017 M to 2017 A
3 | Research proposal | bar: 2017 A to 2017 S
4 | Repulsive Magnetic System Model | bar: 2017 M to 2018 J
4.1 | Literature Review | bar: 2017 J to 2017 A
4.2 | Development | bar: 2017 A to 2017 O
4.3 | Computation | bar: 2017 O to 2017 N
4.4 | Test/ Analysis | bar: 2017 N to 2018 J
4.5 | Report | bar: 2017 D to 2018 J
5 | Control System Development | bar: 2018 F to 2018 S
5.1 | Literature Review | bar: 2018 F to 2018 A
5.2 | Skill Development | bar: 2018 M to 2018 M
5.3 | Implementation | bar: 2018 A to 2018 J
5.4 | Test/ Analysis | bar: 2018 J to 2018 A
5.5 | Report | bar: 2018 A to 2018 S
6 | Prototype of Ocean Wave Harvester | bar: 2018 O to 2019 M
6.1 | Literature Review | bar: 2018 O to 2018 D
6.2 | Consultation with Stakeholders | bar: 2018 N to 2018 D
6.3 | Design Development | bar: 2018 D to 2019 F
6.4 | Prototype Construction | bar: 2019 J to 2019 M
6.5 | Experimentation/ Analysis | bar: 2019 F to 2019 A
6.6 | Report | bar: 2019 A to 2019 M
7 | Prototype of Small Scale Powering Device | bar: 2019 J to 2020 J
7.1 | Feasibility Review based on previous Work | bar: 2019 J to 2019 J
7.2 | Literature Revew | bar: 2019 J to 2019 J
7.3 | Consultation with Stakeholders | bar: 2019 J to 2019 A
7.4 | Design Development | bar: 2019 J to 2019 A
7.5 | Prototype Construction | bar: 2019 A to 2019 N
7.6 | Experimentation/ Analysis | bar: 2019 S to 2019 D
7.7 | Report (Paper) | bar: 2019 N to 2020 J
8 | Thesis | bar: 2019 J to 2020 M
8.1 | Writing/ Editing | bar: 2019 J to 2019 D
8.2 | Review by Supervisors | bar: 2019 N to 2020 J
8.3 | Incorporate Feedback | bar: 2020 J to 2020 M

## Sheet2
o | Highlights a key date which you must comply with.
Time spent on a task - eg. shade Jan X9 to Jun X9 to indicate you will be working on your research proposal.
NB